## Slide 1: Mixed methods evaluation of the Intergenerational Schools Dementia Project
The challenges of working with children (and teachers)
Jennifer Bray

## Slide 2: Project overview
Dementia is a growing global concern
  Between 700,000 and 800,000 people living with dementia in the UK
The Prime Minister’s Challenge on Dementia developed to focus on:
  Driving improvements in health & care
  Creating dementia-friendly communities
  Better research
Intergenerational Schools Dementia Project

## Slide 3: Aims of the project
Four main aims:
  Raise awareness and understanding of dementia
  Appreciate the difficulties of caring for someone with dementia
  Understand the role of assistive and digital technology
  Meet someone with dementia
22 schools engaged in initial pilot phase
  Implement dementia curriculum during 2012/2013 academic year

## Slide 4: The evaluation
How do we measure the impact of the dementia interventions?
  Each school used its own curriculum approach
  Wide range of pupils involved (5-19)
Chose mixed approach
  ‘Pre’ and ‘Post’ questionnaires
  Case studies
Worked with range of people to design tools

## Slide 5: Questionnaires - Planned approach
Primary schools
  Circle time evaluation – one per class
Secondary schools and colleges
  Individual questionnaires – one per pupil
  Online version not practical
Each school provided with questionnaire pack and guidelines
Intended for schools to analyse and report on own results – not feasible

## Slide 6: Challenges encountered by schools
Practical issues
  Who prints out the questionnaires
  Time needed to complete
  Some pupils caught up in exams and other commitments
Some pupils felt that they were being tested
Communication issues
Project managers/ stakeholder group
Schools
Local coordinators
ADS
13 out of 22 schools

## Slide 7: Challenges encountered by us
Timescales
  Different in different schools
  Deadlines changed mid-project
Unhelpful schools
  Difficult to contact, poor communication
Helpful schools
  Added in information which altered layout
Pupils
  Misreading/misunderstanding questions
  Some just not interested

## Slide 8: Practical issues
Number of responses
  Data entry and analysis

## Slide 9: But...
Positive impact of the project
Benefits for pupils
  Increased awareness of dementia
  Reduced fear and stigma
  Appreciate caring role and how to help carers
  Increased awareness of how to help people with dementia to live well
Impact on teachers, whole schools and wider community

## Slide 10: Helped pupils at a personal level
“My grandfather has dementia. I felt very strange with him when I was told because he didn’t seem like my grandfather any more. After these lessons I can understand what it is like for him and have been more able to talk with him and to see that he is still my grandfather”

## Slide 11: Evaluation lessons learnt
Clear lines of communication
  Manage expectations
  Point of contact for teachers
Different approaches for different age groups
Keep questionnaires short and focused
  Appropriate language
  Clear (and fixed) format
  Easy to answer – tick boxes v free text
Realistic timescales
  Work WITH schools

## Slide 12
Thank you for listening!
Jennifer Bray
Association for Dementia Studies
University of Worcester
j.bray@worc.ac.uk
http://www.worc.ac.uk/discover/association-for-dementia-studies.html